## GITHUB_ISSUE_IMPORT
planning_id | title | body | labels | milestone | dependencies
AF-000 | [AF-000] Establish Phase 0 documentation index | ## Objective 创建统一文档入口、阅读顺序和状态声明。 ## Acceptance Criteria - README 链接有效；明确当前无业务代码；禁止虚构已完成指标。 ## Dependencies `None` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:docs,priority:P0,size:S,status:ready | M0 Engineering System | None
AF-001 | [AF-001] Approve project charter | ## Objective 冻结使命、范围、成功标准和角色。 ## Acceptance Criteria - Charter 与 v2.0 一致；明确做/不做；具备变更控制。 ## Dependencies `AF-000` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:docs,type:governance,priority:P0,size:S,status:ready | M0 Engineering System | AF-000
AF-002 | [AF-002] Approve architecture baseline | ## Objective 定义模块化单体、容器、状态所有权和信任边界。 ## Acceptance Criteria - LangGraph/Temporal 边界、State Ownership、Idempotency Contract 明确。 ## Dependencies `AF-001` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:architecture,priority:P0,risk:high,size:M,status:ready | M0 Engineering System | AF-001
AF-003 | [AF-003] Approve quality strategies | ## Objective 建立测试、安全、可靠性和评测基线。 ## Acceptance Criteria - 每类策略有测试层级、Gate、证据和停止条件。 ## Dependencies `AF-002` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:test,type:security,priority:P0,risk:high,size:M,status:ready | M0 Engineering System | AF-002
AF-004 | [AF-004] Establish GitHub governance | ## Objective 建立 Labels、Milestones、Issue/PR 模板和分支策略。 ## Acceptance Criteria - One Issue One PR；Human Merge；模板可用。 ## Dependencies `AF-001` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:governance,priority:P0,size:M,status:ready | M0 Engineering System | AF-001
AF-005 | [AF-005] Establish AI collaboration protocol | ## Objective 约束 AI 多月持续开发。 ## Acceptance Criteria - 定义会话启动、设计、测试、实现、Handoff 和停止条件。 ## Dependencies `AF-001` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:docs,type:ai-process,priority:P0,size:M,status:ready | M0 Engineering System | AF-001
AF-006 | [AF-006] Accept initial ADR set | ## Objective 把冻结范围转化为 ADR。 ## Acceptance Criteria - 至少 12 个 ADR 标记 Accepted。 ## Dependencies `AF-002` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:architecture,priority:P0,size:M,status:ready | M0 Engineering System | AF-002
AF-007 | [AF-007] Create configuration placeholder contract | ## Objective 定义配置项，不写真实密钥。 ## Acceptance Criteria - .env.example 全为占位符；配置所有权明确。 ## Dependencies `AF-003` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:security,type:docs,priority:P0,size:S,status:ready | M0 Engineering System | AF-003
AF-008 | [AF-008] Prepare documentation-only repository scaffold | ## Objective 创建文档目录和 GitHub 模板，不写业务代码。 ## Acceptance Criteria - 仓库只含文档/config templates；manifest 验证无业务代码。 ## Dependencies `AF-000,AF-004,AF-007` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:docs,type:repo,priority:P0,size:S,status:ready | M0 Engineering System | AF-000,AF-004,AF-007
AF-101 | [AF-101] Create modular monolith application skeleton | ## Objective 建立 FastAPI 模块边界和最小 health contract。 ## Acceptance Criteria - 模块目录存在；只有骨架接口；测试先行。 ## Dependencies `AF-008` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:backend,priority:P0,size:M,status:blocked | M1 Demand to Plan | AF-008
AF-102 | [AF-102] Create Docker Compose foundation | ## Objective 建立 Core、PostgreSQL、Redis 本地依赖基础。 ## Acceptance Criteria - 一条命令启动；healthcheck 通过；配置来自占位符。 ## Dependencies `AF-101` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:infra,priority:P0,size:M,status:blocked | M1 Demand to Plan | AF-101
AF-103 | [AF-103] Define initial domain model and migrations | ## Objective 定义 Tenant、Workflow、Run、Step、Approval、Audit 基础模型。 ## Acceptance Criteria - 模型有 tenant_id；版本不可覆盖；迁移测试通过。 ## Dependencies `AF-101,AF-102` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:backend,type:architecture,priority:P0,size:M,status:blocked | M1 Demand to Plan | AF-101,AF-102
AF-104 | [AF-104] Implement Intake Agent contract | ## Objective 标准化 PRD/Bug/Issue 并生成幂等输入。 ## Acceptance Criteria - 结构化 Schema；重复输入识别；单元测试通过。 ## Dependencies `AF-103` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:agent-runtime,pack:delivery,priority:P0,size:M,status:blocked | M1 Demand to Plan | AF-103
AF-105 | [AF-105] Implement Clarifier Agent contract | ## Objective 识别缺失信息并形成澄清问题。 ## Acceptance Criteria - 缺失信息、问题和完成判定结构化；HITL 契约测试。 ## Dependencies `AF-104` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:agent-runtime,pack:delivery,priority:P0,size:M,status:blocked | M1 Demand to Plan | AF-104
AF-106 | [AF-106] Implement Context Agent retrieval contract | ## Objective 检索代码、文档、ADR 和历史 PR。 ## Acceptance Criteria - 输出 Context Package 和引用；无引用结论被标记。 ## Dependencies `AF-103` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:rag,pack:delivery,priority:P0,size:L,status:blocked | M1 Demand to Plan | AF-103
AF-107 | [AF-107] Implement Planner Agent contract | ## Objective 生成架构方案、任务拆分、风险和预算。 ## Acceptance Criteria - Plan Schema 稳定；风险和工具可验证；无副作用。 ## Dependencies `AF-105,AF-106` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:agent-runtime,pack:delivery,priority:P0,size:L,status:blocked | M1 Demand to Plan | AF-105,AF-106
AF-108 | [AF-108] Implement clarification HITL interface | ## Objective 支持 Clarifier 发起和接收人工澄清。 ## Acceptance Criteria - 请求可暂停；回复关联 run；重复回复被拒。 ## Dependencies `AF-105` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:workflow-runtime,priority:P0,size:M,status:blocked | M1 Demand to Plan | AF-105
AF-109 | [AF-109] Add initial Langfuse tracing and cost fields | ## Objective 记录 Agent 节点、Prompt、Token 和成本。 ## Acceptance Criteria - 每节点有 run/agent/prompt/model/token/latency；Secret 脱敏。 ## Dependencies `AF-104,AF-105,AF-106,AF-107` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:observability,priority:P1,size:M,status:blocked | M1 Demand to Plan | AF-104,AF-105,AF-106,AF-107
AF-110 | [AF-110] Build Gate 1A end-to-end test | ## Objective 验证真实需求到带证据方案。 ## Acceptance Criteria - 固定 Fixture 可重复；失败点可定位；输出 Trace。 ## Dependencies `AF-104,AF-105,AF-106,AF-107,AF-108,AF-109` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:test,priority:P0,risk:high,size:L,status:blocked | M1 Demand to Plan | AF-104,AF-105,AF-106,AF-107,AF-108,AF-109
AF-201 | [AF-201] Register GitHub App and verify webhook signature | ## Objective 建立 GitHub 事件入口。 ## Acceptance Criteria - 签名、时间窗口、防重放和失败审计测试通过。 ## Dependencies `AF-102` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:integration,type:security,priority:P0,risk:high,size:M,status:blocked | M2 Plan to Draft PR | AF-102
AF-202 | [AF-202] Implement GitHub MCP read tools | ## Objective 提供仓库、Issue、PR、Diff 只读工具。 ## Acceptance Criteria - Tool Schema、Scope、Timeout、错误映射和审计完整。 ## Dependencies `AF-201` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:mcp,priority:P0,risk:medium,size:L,status:blocked | M2 Plan to Draft PR | AF-201
AF-203 | [AF-203] Implement repository knowledge ingestion | ## Objective 将仓库文档和代码索引到 pgvector。 ## Acceptance Criteria - 增量索引；tenant/repo 隔离；检索基准通过。 ## Dependencies `AF-202,AF-106` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:rag,priority:P0,size:L,status:blocked | M2 Plan to Draft PR | AF-202,AF-106
AF-204 | [AF-204] Implement local Docker sandbox baseline | ## Objective 提供非 root、资源受限、临时工作区执行环境。 ## Acceptance Criteria - 禁止 Docker socket；网络可控；超时和清理测试通过。 ## Dependencies `AF-102` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:sandbox,type:security,priority:P0,risk:high,size:L,status:blocked | M2 Plan to Draft PR | AF-102
AF-205 | [AF-205] Implement Executor Agent contract | ## Objective 根据批准 Plan 在沙箱改码和测试。 ## Acceptance Criteria - 只调用允许工具；产生 Patch/Test/Evidence；失败结构化。 ## Dependencies `AF-107,AF-204` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:agent-runtime,pack:delivery,priority:P0,risk:high,size:L,status:blocked | M2 Plan to Draft PR | AF-107,AF-204
AF-206 | [AF-206] Implement Reviewer Agent contract | ## Objective 汇总 Plan、Patch、测试和证据。 ## Acceptance Criteria - 输出 Decision、Findings、Approval Need；引用可追踪。 ## Dependencies `AF-205` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:agent-runtime,pack:delivery,priority:P0,size:L,status:blocked | M2 Plan to Draft PR | AF-205
AF-207 | [AF-207] Implement deterministic Policy Gate v0 | ## Objective 在 Executor 前做权限、成本和风险规则。 ## Acceptance Criteria - LLM 不可覆盖规则；拒绝有审计；规则有单测。 ## Dependencies `AF-107` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:security,type:policy,priority:P0,risk:high,size:L,status:blocked | M2 Plan to Draft PR | AF-107
AF-208 | [AF-208] Implement GitHub draft pull request tool | ## Objective 创建 Branch、Commit 和 Draft PR。 ## Acceptance Criteria - 写操作有 Scope、审批、幂等和远端 Marker。 ## Dependencies `AF-202,AF-205,AF-206,AF-207` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:mcp,type:integration,priority:P0,risk:high,size:L,status:blocked | M2 Plan to Draft PR | AF-202,AF-205,AF-206,AF-207
AF-209 | [AF-209] Implement webhook and tool-call idempotency | ## Objective 防止重复事件和外部副作用。 ## Acceptance Criteria - 唯一键含 tenant/run/step/tool/args hash；重复 PR 数 0。 ## Dependencies `AF-201,AF-208` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:reliability,priority:P0,risk:high,size:L,status:blocked | M2 Plan to Draft PR | AF-201,AF-208
AF-210 | [AF-210] Build Gate 1B end-to-end test | ## Objective 验证方案到 Draft PR。 ## Acceptance Criteria - 测试仓库完成沙箱改码、Review、审批和 Draft PR。 ## Dependencies `AF-203,AF-204,AF-205,AF-206,AF-207,AF-208,AF-209` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:test,priority:P0,risk:high,size:XL,status:blocked | M2 Plan to Draft PR | AF-203,AF-204,AF-205,AF-206,AF-207,AF-208,AF-209
AF-211 | [AF-211] Record Gate 1 demo and evidence report | ## Objective 固化 Gate 1 证据。 ## Acceptance Criteria - 视频、Trace、成本和失败说明归档；不夸大。 ## Dependencies `AF-110,AF-210` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:docs,type:demo,priority:P0,size:M,status:blocked | M2 Plan to Draft PR | AF-110,AF-210
AF-301 | [AF-301] Bootstrap Temporal workflow and worker | ## Objective 建立外层 durable workflow。 ## Acceptance Criteria - Workflow/Activity 分离；replay-safe；测试环境可启动。 ## Dependencies `AF-210` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:workflow-runtime,priority:P0,risk:high,size:L,status:blocked | M3 Reliable Runtime | AF-210
AF-302 | [AF-302] Enforce runtime state ownership boundaries | ## Objective 分离 Temporal、LangGraph、PostgreSQL、Redis 状态。 ## Acceptance Criteria - 无双重 retry；状态表与实现一致。 ## Dependencies `AF-301` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:architecture,type:reliability,priority:P0,risk:high,size:M,status:blocked | M3 Reliable Runtime | AF-301
AF-303 | [AF-303] Add LangGraph PostgresSaver checkpoints | ## Objective 持久化 Agent 图状态。 ## Acceptance Criteria - 节点后 checkpoint；resume 测试；tenant/run 唯一定位。 ## Dependencies `AF-302` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:agent-runtime,type:reliability,priority:P0,size:L,status:blocked | M3 Reliable Runtime | AF-302
AF-304 | [AF-304] Implement durable clarification signal | ## Objective 澄清等待由 Temporal Signal 管理。 ## Acceptance Criteria - 跨 worker 重启等待和恢复；重复 signal 可处理。 ## Dependencies `AF-301,AF-108` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:workflow-runtime,priority:P0,size:M,status:blocked | M3 Reliable Runtime | AF-301,AF-108
AF-305 | [AF-305] Implement durable approval signal | ## Objective 高风险审批可长时间等待。 ## Acceptance Criteria - 批准/拒绝持久；过期和重复决策有测试。 ## Dependencies `AF-301,AF-207` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:workflow-runtime,type:security,priority:P0,risk:high,size:M,status:blocked | M3 Reliable Runtime | AF-301,AF-207
AF-306 | [AF-306] Define activity retry and timeout policies | ## Objective 按错误类型设置 retry/timeout。 ## Acceptance Criteria - 429、5xx、权限、测试失败和不可逆错误策略不同。 ## Dependencies `AF-301` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:reliability,priority:P0,risk:high,size:M,status:blocked | M3 Reliable Runtime | AF-301
AF-307 | [AF-307] Implement idempotency ledger | ## Objective 持久记录外部副作用执行。 ## Acceptance Criteria - 唯一约束、状态机、结果重用和并发测试通过。 ## Dependencies `AF-209,AF-301` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:reliability,type:database,priority:P0,risk:high,size:L,status:blocked | M3 Reliable Runtime | AF-209,AF-301
AF-308 | [AF-308] Implement Saga compensation | ## Objective 补偿 Branch、Draft PR 和临时资源。 ## Acceptance Criteria - 补偿可重复；失败升级人工；审计完整。 ## Dependencies `AF-306,AF-307` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:reliability,priority:P1,risk:high,size:L,status:blocked | M3 Reliable Runtime | AF-306,AF-307
AF-309 | [AF-309] Create kill-worker fault injection harness | ## Objective 重复终止 worker 并测量恢复。 ## Acceptance Criteria - 20 次测试；记录恢复和重复副作用；可复现。 ## Dependencies `AF-303,AF-304,AF-305,AF-307` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:test,type:reliability,priority:P0,risk:high,size:L,status:blocked | M3 Reliable Runtime | AF-303,AF-304,AF-305,AF-307
AF-310 | [AF-310] Implement LiteLLM model gateway | ## Objective 统一模型接口、预算和成本。 ## Acceptance Criteria - 主/备配置为 Secret 引用；记录模型版本和成本。 ## Dependencies `AF-109` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:model-gateway,priority:P0,size:L,status:blocked | M3 Reliable Runtime | AF-109
AF-311 | [AF-311] Implement circuit breaker and fallback | ## Objective 主模型故障时熔断降级。 ## Acceptance Criteria - Closed/Open/Half-Open 测试；Trace 显示路由链。 ## Dependencies `AF-310` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:model-gateway,type:reliability,priority:P0,risk:high,size:L,status:blocked | M3 Reliable Runtime | AF-310
AF-312 | [AF-312] Publish Gate 2 reliability report and blog | ## Objective 形成可靠性证据和语义/源码研究记录。 ## Acceptance Criteria - 报告含环境、20 次结果、限制和真实证据。 ## Dependencies `AF-309,AF-311` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:docs,type:demo,priority:P0,size:L,status:blocked | M3 Reliable Runtime | AF-309,AF-311
AF-401 | [AF-401] Implement tenant domain and isolation filter | ## Objective 所有业务访问绑定 tenant。 ## Acceptance Criteria - 缺失 tenant 被拒；查询自动过滤；隔离测试准备完成。 ## Dependencies `AF-103` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:security,type:backend,priority:P0,risk:high,size:L,status:blocked | M4 Governance & Security | AF-103
AF-402 | [AF-402] Integrate OIDC authentication | ## Objective 使用外部 OIDC，不自建密码。 ## Acceptance Criteria - Issuer/Client 为占位配置；Token 验证测试通过。 ## Dependencies `AF-401` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:security,type:identity,priority:P0,risk:high,size:L,status:blocked | M4 Governance & Security | AF-401
AF-403 | [AF-403] Implement RBAC | ## Objective 建立 Admin/Developer/Reviewer/Security/DevOps/Viewer。 ## Acceptance Criteria - API 和 Tool 权限映射；拒绝测试完整。 ## Dependencies `AF-402` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:security,type:rbac,priority:P0,risk:high,size:L,status:blocked | M4 Governance & Security | AF-402
AF-404 | [AF-404] Implement contextual policy rules | ## Objective 结合角色、tenant、repo、environment、risk、approval。 ## Acceptance Criteria - 不构建通用 ABAC；确定性规则可解释。 ## Dependencies `AF-403,AF-207` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:security,type:policy,priority:P0,risk:high,size:L,status:blocked | M4 Governance & Security | AF-403,AF-207
AF-405 | [AF-405] Implement append-only audit log | ## Objective 记录权限、审批、工具和安全事件。 ## Acceptance Criteria - 普通用户不可删；actor/action/resource/decision/reason/trace 完整。 ## Dependencies `AF-403,AF-404` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:security,type:audit,priority:P0,risk:high,size:L,status:blocked | M4 Governance & Security | AF-403,AF-404
AF-406 | [AF-406] Implement MCP registry with scopes | ## Objective 统一注册工具、版本、Scope 和风险。 ## Acceptance Criteria - 未注册/未授权工具被拒；Token 不透传；审计完整。 ## Dependencies `AF-202,AF-403,AF-404` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:mcp,type:security,priority:P0,risk:high,size:L,status:blocked | M4 Governance & Security | AF-202,AF-403,AF-404
AF-407 | [AF-407] Harden Docker sandbox | ## Objective 强化文件系统、网络和资源限制。 ## Acceptance Criteria - 负向测试通过；Secret 不进 workspace；自动清理。 ## Dependencies `AF-204` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:sandbox,type:security,priority:P0,risk:high,size:L,status:blocked | M4 Governance & Security | AF-204
AF-408 | [AF-408] Implement prompt injection detection | ## Objective 识别 RAG 中诱导越权内容。 ## Acceptance Criteria - 注入被标记；Policy 拒绝高危工具；审计有证据。 ## Dependencies `AF-404,AF-405,AF-406` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:security,type:agent-safety,priority:P0,risk:high,size:L,status:blocked | M4 Governance & Security | AF-404,AF-405,AF-406
AF-409 | [AF-409] Build cross-tenant isolation suite | ## Objective 证明 Tenant A 无法访问 B。 ## Acceptance Criteria - API、DB、RAG、Trace、Tool 全覆盖。 ## Dependencies `AF-401,AF-403,AF-405` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:test,type:security,priority:P0,risk:high,size:L,status:blocked | M4 Governance & Security | AF-401,AF-403,AF-405
AF-410 | [AF-410] Implement immutable prompt versioning | ## Objective Prompt 不可原地修改，Run 固定版本。 ## Acceptance Criteria - 新版本、回滚、审计和 run 关联测试通过。 ## Dependencies `AF-103` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:control-plane,priority:P1,size:M,status:blocked | M4 Governance & Security | AF-103
AF-411 | [AF-411] Implement immutable workflow versioning | ## Objective Workflow 版本不可变。 ## Acceptance Criteria - 旧 Run 可重放；升级不影响在途流程。 ## Dependencies `AF-103,AF-301` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:control-plane,priority:P1,size:M,status:blocked | M4 Governance & Security | AF-103,AF-301
AF-412 | [AF-412] Build governance security regression suite | ## Objective 统一验证 RBAC、Policy、Audit、Injection、Sandbox。 ## Acceptance Criteria - 正向/负向/越权/重放测试可重复。 ## Dependencies `AF-403,AF-404,AF-405,AF-406,AF-407,AF-408,AF-409` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:test,type:security,priority:P0,risk:high,size:XL,status:blocked | M4 Governance & Security | AF-403,AF-404,AF-405,AF-406,AF-407,AF-408,AF-409
AF-413 | [AF-413] Record Gate 3 governance demo | ## Objective 固化注入拦截和跨租户证据。 ## Acceptance Criteria - 视频、测试日志、审计和限制完整。 ## Dependencies `AF-412` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:docs,type:demo,priority:P0,size:M,status:blocked | M4 Governance & Security | AF-412
AF-501 | [AF-501] Create Golden Dataset framework | ## Objective 定义 Dataset、Case、Expected、Run、Metric。 ## Acceptance Criteria - 可版本化、可重复、可比较；无真实 Secret。 ## Dependencies `AF-410,AF-411` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:evaluation,priority:P0,size:L,status:blocked | M5 Evaluation & Deployment | AF-410,AF-411
AF-502 | [AF-502] Select SWE-bench Verified Python subset | ## Objective 选择 10–15 个真实 Issue-Patch。 ## Acceptance Criteria - 选择标准、许可证、成本和限制有文档。 ## Dependencies `AF-501` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:evaluation,priority:P1,size:M,status:blocked | M5 Evaluation & Deployment | AF-501
AF-503 | [AF-503] Create security injection dataset | ## Objective 创建 15–20 个真值安全案例。 ## Acceptance Criteria - 覆盖 SQL 注入、Secret、Token、越权、Prompt Injection。 ## Dependencies `AF-408,AF-501` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:evaluation,type:security,priority:P0,risk:high,size:L,status:blocked | M5 Evaluation & Deployment | AF-408,AF-501
AF-504 | [AF-504] Create historical bug dataset | ## Objective 整理 XueMai/SynTour 历史问题。 ## Acceptance Criteria - 5–10 个脱敏 Case；真值、修复和来源完整。 ## Dependencies `AF-501` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:evaluation,priority:P1,size:M,status:blocked | M5 Evaluation & Deployment | AF-501
AF-505 | [AF-505] Implement single-agent baseline | ## Objective 建立 Full AegisFlow 对照。 ## Acceptance Criteria - 同任务、同模型、同预算；比较完成率/成本/越权/延迟。 ## Dependencies `AF-501` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:evaluation,priority:P1,size:L,status:blocked | M5 Evaluation & Deployment | AF-501
AF-506 | [AF-506] Implement evaluation metrics and report | ## Objective 计算完成率、Tool Success、检出、误报、Patch、成本、p95。 ## Acceptance Criteria - 报告显示分子分母；小样本不只写百分比。 ## Dependencies `AF-502,AF-503,AF-504,AF-505` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:evaluation,priority:P0,size:L,status:blocked | M5 Evaluation & Deployment | AF-502,AF-503,AF-504,AF-505
AF-507 | [AF-507] Add prompt regression gate to CI | ## Objective Prompt 退化时阻止发布。 ## Acceptance Criteria - 阈值配置化；失败有报告；可回滚。 ## Dependencies `AF-506` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:evaluation,type:ci,priority:P0,risk:high,size:L,status:blocked | M5 Evaluation & Deployment | AF-506
AF-508 | [AF-508] Instrument system traces with OTel | ## Objective 追踪 API、Temporal、DB、MCP、Sandbox。 ## Acceptance Criteria - trace/run/tenant 贯通；敏感字段脱敏。 ## Dependencies `AF-301,AF-406` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:observability,priority:P0,size:L,status:blocked | M5 Evaluation & Deployment | AF-301,AF-406
AF-509 | [AF-509] Expose Prometheus metrics | ## Objective 暴露成功、失败、成本、延迟、队列和资源。 ## Acceptance Criteria - 命名、Label Cardinality 和测试符合规范。 ## Dependencies `AF-508` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:observability,priority:P0,size:M,status:blocked | M5 Evaluation & Deployment | AF-508
AF-510 | [AF-510] Build Grafana dashboards | ## Objective 展示 Gate 数字。 ## Acceptance Criteria - 成功率、成本、p95、失败节点、Fallback、人工介入可见。 ## Dependencies `AF-509,AF-506` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:observability,priority:P0,size:M,status:blocked | M5 Evaluation & Deployment | AF-509,AF-506
AF-511 | [AF-511] Run 100-concurrent-user load test | ## Objective Locust 测试控制面。 ## Acceptance Criteria - 环境、场景、p50/p95/p99、错误率、资源和限制有报告。 ## Dependencies `AF-509` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:performance,type:test,priority:P0,risk:medium,size:L,status:blocked | M5 Evaluation & Deployment | AF-509
AF-512 | [AF-512] Create k3s demo environment | ## Objective 建立演示集群。 ## Acceptance Criteria - 配置无 Secret；Core/Worker/Observability 可运行。 ## Dependencies `AF-413` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:infra,priority:P1,risk:medium,size:L,status:blocked | M5 Evaluation & Deployment | AF-413
AF-513 | [AF-513] Create Helm chart | ## Objective 打包演示部署。 ## Acceptance Criteria - values 为占位符；upgrade/rollback 测试通过。 ## Dependencies `AF-512` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:infra,priority:P0,size:L,status:blocked | M5 Evaluation & Deployment | AF-512
AF-514 | [AF-514] Implement read-only workflow run graph | ## Objective 只读展示节点状态。 ## Acceptance Criteria - 节点、状态、耗时、Trace 和失败原因可见。 ## Dependencies `AF-508` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:frontend,priority:P1,size:L,status:blocked | M5 Evaluation & Deployment | AF-508
AF-515 | [AF-515] Build thin Personal Workbench flows | ## Objective 接入 XueMai、SynTour、Omni-Assistant 和实习跟踪。 ## Acceptance Criteria - 只复用平台能力；不新增通用助手方向。 ## Dependencies `AF-513,AF-514` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | pack:personal,priority:P2,size:L,status:blocked | M5 Evaluation & Deployment | AF-513,AF-514
AF-516 | [AF-516] Complete README, reports and demo package | ## Objective 生成面试证据包。 ## Acceptance Criteria - 中英 README、Architecture、ADR、Evaluation、Reliability、Load、Threat Model 齐全。 ## Dependencies `AF-506,AF-510,AF-511,AF-513` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:docs,type:demo,priority:P0,size:L,status:blocked | M5 Evaluation & Deployment | AF-506,AF-510,AF-511,AF-513
AF-517 | [AF-517] Execute Gate 4 final acceptance | ## Objective 完成四个必做演示和 Gate 验收。 ## Acceptance Criteria - 现场复现；结果记录；未达项不得伪装。 ## Dependencies `AF-507,AF-510,AF-511,AF-513,AF-516` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:release,priority:P0,risk:high,size:L,status:blocked | M5 Evaluation & Deployment | AF-507,AF-510,AF-511,AF-513,AF-516
AF-R01 | [AF-R01] Build single-scenario OpsPilot simulation | ## Objective Gate 1–4 后增加一个模拟事故场景。 ## Acceptance Criteria - 只用模拟数据；不改主叙事；独立 ADR。 ## Dependencies `AF-517` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:roadmap,pack:opspilot,priority:P3,size:XL,status:blocked | Post-MVP Roadmap | AF-517
AF-R02 | [AF-R02] Add optional vLLM fallback | ## Objective 有 GPU 时加入本地模型。 ## Acceptance Criteria - 可选开关；不阻塞系统；成本和性能有测量。 ## Dependencies `AF-517` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:roadmap,type:model-gateway,priority:P3,size:L,status:blocked | Post-MVP Roadmap | AF-517
AF-R03 | [AF-R03] Add MCP integrations from dogfooding | ## Objective 只按真实需求增加工具。 ## Acceptance Criteria - 每个工具有场景、Scope、Policy、Audit 和测试。 ## Dependencies `AF-515` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:roadmap,type:mcp,priority:P3,size:L,status:blocked | Post-MVP Roadmap | AF-515
AF-212 | [AF-212] Adopt run progress delivery ADR | ## Objective 决定长任务运行进度如何送达 Console，并记录为 ADR-0013。交付流程包含澄清与审批等待，进度传递方式必须先有决策，不得留白。 ## Acceptance Criteria - ADR-0013 记录轮询与 SSE 的取舍、选定方案与触发升级阈值； - MVP 阶段采用轮询，明确刷新间隔与 run 状态字段来源； - 若未来启用 SSE，ADR 需预先写明续传契约（event id 与 checkpoint 关联）； - 不实现任何流式传输代码。 ## Dependencies `AF-210` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:architecture,type:docs,priority:P0,size:S,status:blocked | M2 Plan to Draft PR | AF-210
AF-213 | [AF-213] Start continuous dogfooding on owned repository | ## Objective 在 Gate 1 通过后立即开始对自有仓库持续投喂真实需求，产生长期真实运行数据、成本样本与失败案例，而不是等到 M5 才开始使用。 ## Acceptance Criteria - 指定一个自有仓库作为 dogfooding 目标，仅使用只读与 Draft PR 能力； - 每周至少投入 3 个真实需求并记录 run id； - 建立 dogfooding 运行日志文件，记录需求、结果、失败原因与人工干预次数； - 不引入新功能代码；不接触生产环境；不使用真实密钥。 ## Dependencies `AF-210,AF-211` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | pack:personal,type:process,priority:P0,size:M,status:blocked | M2 Plan to Draft PR | AF-210,AF-211
AF-313 | [AF-313] Implement layered agent memory | ## Objective 实现工作记忆与长期记忆的分层结构，并明确其状态所有权，避免与 Temporal / LangGraph checkpoint 重复持有同一状态。 ## Acceptance Criteria - 工作记忆归属 LangGraph checkpoint，长期记忆归属 PostgreSQL，边界写入 Design Note； - 长期记忆写入是幂等的，重放不产生重复条目； - 记忆读写受 tenant 隔离约束； - 不违反 ADR-0002；Redis 不作为记忆事实源； - 提供 replay 场景测试：同一 run 重放后记忆内容一致。 ## Dependencies `AF-303,AF-307` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:agent-runtime,type:reliability,priority:P0,risk:high,size:L,status:blocked | M3 Reliable Runtime | AF-303,AF-307
AF-314 | [AF-314] Implement context compaction policy | ## Objective 实现上下文压缩策略，控制长交付流程中的 token 增长，并使压缩带来的信息损失可观测、可评估。 ## Acceptance Criteria - 压缩触发条件是确定性的（token 阈值或轮次阈值），不由模型自行决定； - 采用增量摘要，保留决策类信息，压缩前后均落 Trace； - 压缩前后的 token 数与保留要点数作为指标上报； - 提供压缩导致关键信息丢失的负向测试； - 压缩策略版本化，可与 Prompt 版本一同回归。 ## Dependencies `AF-313,AF-109` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:agent-runtime,type:evaluation,priority:P0,risk:high,size:L,status:blocked | M3 Reliable Runtime | AF-313,AF-109
AF-414 | [AF-414] Implement tenant-scoped API rate limiting | ## Objective 在控制面实现租户级限流与配额，使并发压测结果能够反映治理能力，而不仅是吞吐量。 ## Acceptance Criteria - 限流键包含 tenant 与主体身份，配置可按租户覆盖； - 超限返回标准错误并写入审计，不静默丢弃； - 限流状态存于 Redis，但配额定义的事实源在 PostgreSQL； - 提供超限负向测试与跨租户互不影响测试； - 与 AF-511 压测联动，报告中区分被限流请求与失败请求。 ## Dependencies `AF-403,AF-311` ## Required Process - [ ] Read relevant architecture and ADR documents - [ ] Create or update Design Note - [ ] Define tests before implementation - [ ] Confirm security impact - [ ] Implement the smallest acceptable change - [ ] Run tests and quality gates - [ ] Update documentation and traceability matrix - [ ] Open one PR linked to this Issue - [ ] Wait for human review and merge ## Secret Handling Use placeholders only. Do not request or expose real credentials in this Issue. | type:security,type:reliability,priority:P0,risk:high,size:M,status:blocked | M4 Governance & Security | AF-403,AF-311